## Template
|  |  | Owner | Q1 | Q2 | Q3 | Q4
Vision/Project Title in here | #1 | Workstream 1 Title
| #2 | Workstream 2 Title
| #3 | Workstream 3 Title
| #4 | Workstream 4 Title
| #5 | Workstream 5 Title
| #6 | Workstream 6 Title

## Example 1
|  |  | Owner | Q1 |  |  |  | Q2 |  |  |  | Q3 |  | Q4
Relocation Project | #1 | Relocate Head Office | BC | Planning | Move to new site
| #2 | Relocate IT Office | DE |  |  |  |  | Planning | Move to new site
| #3 | Relocate small animals | FG |  |  |  |  | Planning | Move cats | Move dogs | Move amphibians
| #4 | Relocate large animals | HI | [7 empty] | Planning | Move goats | Move other large animals
| #5 | Relocate warehouse and stock | JK | Planning | Acquire new building | Equip new building | Move to new warehouse | All suppliers updated
| #6 | Close down old buildings | LM |  |  |  |  | Planning | Close down old Head Office |  |  | Close down old IT office |  | Close down small animal building | Close down large animal building | Close out old warehouse

## Example 2
|  |  | Owner | Q1 |  | Q2 |  |  |  | Q3 |  | Q4
Go Digital | #1 | Understand the paper | BC | Planning | Process mapping
| #2 | IT transformation | DE | Wifi project | Infrastructure project | Single sign on project | Intranet project |  |  | Digital Project 1 | Digital Project 2
| #3 | People workstream | FG | Training needs assessment |  | Collaboration tool project | Training design | Recruitment | Staff onboarding process | Training Phase 1 | Training Phase 2 | Training Phase 3
| #4 | Compliance workstream | HI |  |  | Regulation X compliance project |  |  |  | Policy review and update |  | Policy review and update
| #5 | Cost saving of £1m | LM | Standard processes Phase 1 | Online payments | Standard processes Phase 2 | Digital archiving project |  |  | Standard processes Phase 3 | Paper destruction project | Standard processes Phase 4